## Sheet1
Gantt Chart for Devolepment of UTM Cafeteria Management System
TASK | TIMELINE
| WEEK 1 |  |  | WEEK 2 |  |  |  | WEEK 3 |  |  | WEEK 4 |  |  | WEEK 5 | WEEK 6 |  | WEEK 7 |  |  | WEEK 8 |  |  | WEEK 9
Define project scope and objectives | 12/5/2025 - 14/5/2025 DANISH
Identify key stakeholders |  | 14/5/2025 - 16/5/2025 ABDURRAFIQ
Develop project schedule and milestone |  |  | 16/5/2025 - 19/52025 MUNIF
Allocate resources and assign roles |  |  |  |  | 19/5/2025 - 20/5/2025 DANIEL
Conduct stakeholder interviews and surveys |  |  |  |  | 19/5/2025 - 22/5/2025 ABBDURRAFIQ
Analyze current cafeteria operations and pain points | [5 empty] | 22/5/2025 - 24/5/2025 DANISH
Document functional and non-functional requirements | [6 empty] | 24/5/2025 - 26/5/2025 DANIEL
Validate and approve requirement specifications | [7 empty] | 26/5/2025 - 27/5/2025 MUNIF
Design system architecture | [7 empty] | 27/5/2025 - 29/5/2025 ABBDURRAFIQ
Create UI/UX prototypes | [8 empty] | 29/5/2025 - 31/5/2025 MUNIF
Design database schema and data flow | [9 empty] | 31/5/2025 - 1/5/2025 DANIEL
Review and finalize design with stakeholders | [11 empty] | 1/6/2025 - 2/6/2025 DANISH
Setup development environment and tools | [11 empty] | 1/6/2025 - 2/6/2025 MUNIF
Develop frontend | [12 empty] | 2/6/2025 - 12/6/2025 DANISH AND ABDURRAFIQ
Develop backend logic | [13 empty] | 5/6/2025 - 15/6/2026 MUNIF AND DANIEL
Integrate payment system and UTM authentication | [14 empty] | 15/6/2025 - 20/6/2025 DANISH AND ABDURRAFIQ
Perform internal code review and unit testing | [15 empty] | 20/6/2025 - 22/6/2025 DANIEL
Develop test plan and detailed test cases | [16 empty] | 22/6/2025 - 25/6/2025 MUNIF
Perform integration and system testing | [17 empty] | 25/6/2026 - 28/5/2025 ABDURRAFIQ
Conduct User Acceptance Testing (UAT) | [18 empty] | 28/6/2025 - 29/6/2025 DANIEL
Fix bugs and optimize performance | [18 empty] | 28/6/2025 - 30/6/2025 DANISH
Prepare deployment plan and rollback procedures | [20 empty] | 30/6/2025 - 3/7/2025 ABDURAFFIQ
Conduct training sessions for staff and users | [21 empty] | 3/7/2025 - 6/7/2025 MUNIF
Deploy to live environment and monitor initial usage | [23 empty] | 6/7/2025 - 8/7/2025 DANISH
Provide user support and gather feedback | [24 empty] | 8/7/2025 - 11/72025 DANIEL